## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
-YaX45NVBEuQ9RiXgqQu1ckAKNcu | Test yield prediction model | Testing & Evaluation Phase | Completed | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 08/03/2026 | 02/01/2026 | 04/01/2026 | false | false | 19/03/2026 | Niwantha W.P.I it21239366
0LTIFJDHlEKXaCo5stLcW8kAJiFR | UAT with farmers | Testing & Evaluation Phase | Not started | Medium | FERNANDO W.T.T.S. it22590244 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 04/04/2026 | false | false
0w11NnKnJUySpzMbYdHlh8kABpYa | Proposal Presentation | Research & Planning Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 | 07/09/2025 | 10/09/2025 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
14jO9rcpJ0KVGwazdxlWaskAJsN0 | Automate notification system (SMS/app) | System Design & Development Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244 | Niwantha W.P.I it21239366 | 08/03/2026 | 17/02/2026 | 21/02/2026 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
16ulC4eHrEyqljJrv3dyhckAOKuf | Project Chater | Research & Planning Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 | 17/07/2025 | 23/07/2025 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
1TrKM93WnkKh43t806XtMMkAAMSP | Research on irrigation methods | Research & Planning Phase | Completed | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 02/09/2025 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674
1Wwsce00wUuae-LXb2qFNckAF-lM | Research crop yield prediction models and best practices for advisory | Research & Planning Phase | Completed | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 08/03/2026 | 01/09/2025 | 02/09/2025 | false | false | 08/03/2026 | Niwantha W.P.I it21239366
3A81oD8bpkS8mPePXxKgbMkAGtn6 | Develop health scoring model | Model Development Phase | Completed | Medium | SANKALPA T W K S D it22564290 | Niwantha W.P.I it21239366 | 08/03/2026 | 05/02/2026 | 05/02/2026 | false | false | 19/03/2026 | SANKALPA T W K S D it22564290
3OjVLGryCk-8l0CsJqZZW8kACY21 | Refine irrigation scheduling algorithms | Testing & Evaluation Phase | Completed | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 02/12/2025 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674
3_eo0-K_b0WEvNOjHWOecMkADEfT | Research paper submission | Research & Planning Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 |  | 04/05/2026 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674
42onAeBinUG_EUMP8-X53skABQBD | Test health scoring system for accuracy | Testing & Evaluation Phase | Completed | Medium | SANKALPA T W K S D it22564290 | Niwantha W.P.I it21239366 | 08/03/2026 | 05/02/2026 | 22/02/2026 | false | false | 19/03/2026 | SANKALPA T W K S D it22564290
5eDIMIY-5UumgnBkXQTNJckAFpWN | Finalize dataset for Crop Advisory & Yield Prediction Engine | Research & Planning Phase | Completed | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 07/03/2026 | 02/01/2026 | 03/01/2026 | false | false | 19/03/2026 | Niwantha W.P.I it21239366
6O3Oah85TEi7bqfUOBw-5MkAAeJc | Finalize dataset for Irrigation Recomandation engine | Research & Planning Phase | Completed | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 |  | 03/01/2026 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674
C1PBv7LHb0SdhOLB-_ukKskAO2X2 | Develop machine learning models for yield prediction | Model Development Phase | Completed | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 08/03/2026 | 07/12/2025 | 10/12/2025 | false | false | 17/03/2026 | Niwantha W.P.I it21239366
CB5CWPSK6U-dHR58H8NYN8kACbhQ | Develop an interactive dashboard for plantation health | System Design & Development Phase | Completed | Medium | SANKALPA T W K S D it22564290 | Niwantha W.P.I it21239366 | 08/03/2026 | 12/11/2025 | 22/12/2025 | false | false | 19/03/2026 | SANKALPA T W K S D it22564290
CBfvqPEsbE-chiqb4xbmHskAFUAx | Collect historical data for model training | Model Development Phase | Completed | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 08/03/2026 | 21/12/2025 | 28/12/2025 | false | false | 19/03/2026 | Niwantha W.P.I it21239366
EpTfqXdRBEmhKAb8rvReQskAKT7d | Complete literature review | Research & Planning Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 | 01/06/2025 | 02/06/2025 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
EuaFEUjjoUmrJ0SdcSyUi8kABBBE | Integrate sensor data into the irrigation model | System Design & Development Phase | Not started | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 20/11/2025 | false | true | 08/03/2026
F3_4P_RXSUOwMQ00aP8GlskAFahg | Conduct team performance reviews | No Bucket | Completed | Important | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 | 01/03/2026 | 07/03/2026 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244 |  |  | Yellow
GJtLd1KEQk2mKhfB6XD718kAGGOW | Report monthly status | No Bucket | Not started | Medium |  | SANKALPA T W K S D it22564290 | 19/03/2026 |  | 08/10/2026 | true | false
HVxcLWAYR0uJvS4wgwfYnckADMYB | Final Presentation & Viva | Research & Planning Phase | Not started | Medium | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 |  | 27/04/2026 | false | false
HtT-5zgnwk-f1Dw-9SOGpckAPJ86 | UAT with farmers | Testing & Evaluation Phase | In progress | Medium | SANKALPA T W K S D it22564290 | Niwantha W.P.I it21239366 | 08/03/2026 | 06/03/2026 | 04/04/2026 | false | false
JA2-PqHFMEanTO7-pomjLskAB2fm | Develop machine learning model for irrigation needs | Model Development Phase | Completed | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 20/11/2025 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674
NLGG13YKQUSBVLA263b7i8kAAAp9 | Proposal Presentation - 1 | Research & Planning Phase | Completed | Important | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 | 05/01/2026 | 05/01/2026 | false | false | 08/03/2026 | Niwantha W.P.I it21239366
QdGsuiJnXE6aBVBfu-4ncckAO__i | Define the scope of the research | Research & Planning Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 | 10/05/2025 | 15/05/2025 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
QzPXfmxOUki8bhnqnXb6wckAPDJ6 | Final Report Submission | Research & Planning Phase | Completed | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 |  | 26/04/2026 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674
Rm57E0UkIE2l2ikaOhZAJ8kACXVT | User Acceptance Testing (UAT) with farmers | Testing & Evaluation Phase | Completed | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 05/04/2026 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674
SXRoGvKyHEqWKclCX2d8eskAB4-_ | Test system for accuracy | Testing & Evaluation Phase | Completed | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 01/12/2025 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674
SiDcWb00cEuP-BYoqebhrskALAVZ | Final adjustments and integration | System Design & Development Phase | Not started | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 11/04/2026 | false | false | 08/03/2026
T2f4YcN9z0CKvypWvndwkskAHHLo | Finalize dataset for Nutrient Deficiency & Fertilizer Recommendation | Research & Planning Phase | Completed | Medium | SANKALPA T W K S D it22564290 | Niwantha W.P.I it21239366 | 07/03/2026 | 19/02/2026 | 19/02/2026 | false | false | 19/03/2026 | SANKALPA T W K S D it22564290
V5q6q9kpk0Gk8sAQDkJGK8kAElN8 | Refine the model and develop user interface | System Design & Development Phase | Completed | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 08/03/2026 | 02/01/2026 | 04/01/2026 | false | false | 19/03/2026 | Niwantha W.P.I it21239366
WLEouga-4Uy5wso2yqcdEskAFJ5l | Website evelution & logbook submission | Research & Planning Phase | Completed | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 |  | 30/04/2026 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674
YRIExoDVck-GdPO-4aWNI8kAEVui | Final optimization and adjustments | System Design & Development Phase | Not started | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 05/04/2026 | false | false
_RKdd5fDtU-zf0_3pbH6hMkAFgjP | Research on health scoring systems and relevant factors | Research & Planning Phase | Completed | Medium | SANKALPA T W K S D it22564290 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 06/09/2025 | false | false | 19/03/2026 | SANKALPA T W K S D it22564290
diQm7Akqg0azwNtCgN8kJskAKaIm | Final Checklist Submission | Research & Planning Phase | In progress | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 07/03/2026 | 08/03/2026 | 30/04/2026 | false | false
eYhZ5MIJlEyDXF-ps4QD5skAL7pV | Research disease detection algorithms and image recognition | Research & Planning Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244 | Niwantha W.P.I it21239366 | 08/03/2026 | 15/08/2025 | 30/08/2025 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
erU-jJtQo0CADtIGjQVCO8kABdxD | Final adjustments and optimization | System Design & Development Phase | Completed | Medium | SANKALPA T W K S D it22564290 | Niwantha W.P.I it21239366 | 08/03/2026 | 05/03/2026 | 11/04/2026 | false | false | 19/03/2026 | SANKALPA T W K S D it22564290
f4tf7S-aVU6CLYMthqAQnskAMmdw | Perform integration with backend and database | System Design & Development Phase | Completed | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 08/03/2026 | 03/01/2026 | 04/01/2026 | false | false | 19/03/2026 | Niwantha W.P.I it21239366
ieTm-JMOj02yI5N6EImeIMkAKEF- | Report monthly status | No Bucket | Completed | Medium |  | SANKALPA T W K S D it22564290 | 19/03/2026 |  | 08/09/2026 | false | false | 19/03/2026 | SANKALPA T W K S D it22564290
iuYcwi8D6EyoSyYSoqCwbMkAHu6n | Data preprocessing and cleaning | Model Development Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 | 02/01/2026 | 05/01/2026 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
jQCTQ46JdkabE1FiBT2pLMkAB0JN | Check List 1 submission | Research & Planning Phase | Completed | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 07/03/2026 |  | 15/12/2025 | false | false | 08/03/2026 | Niwantha W.P.I it21239366
jk0pSy6BXEOYqUQm6IpMdskAIhBM | Finalize dataset for Disease Detection & Notification System | Research & Planning Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244 | Niwantha W.P.I it21239366 | 07/03/2026 | 18/02/2026 | 25/02/2026 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
kViU7DNl70qn0Y_95-40VMkAMOad | Develop and train models to detect diseases and pests | Model Development Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244 | Niwantha W.P.I it21239366 | 08/03/2026 | 02/12/2025 | 06/12/2025 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
lgBXBCQdGk-X39Wzgh4BRMkAH8Xg | Set up a notification system for farmer alerts | System Design & Development Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244 | Niwantha W.P.I it21239366 | 08/03/2026 | 02/12/2025 | 06/12/2025 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
m2s8Lsl-dkiy2t29QfN0z8kADJia | Final adjustments and integration | System Design & Development Phase | Not started | Medium | FERNANDO W.T.T.S. it22590244 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 11/04/2026 | false | false
o_sMHfYrKU6lnrXGnvf4iMkAIrJW | Integrate disease detection system with backend | System Design & Development Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244 | Niwantha W.P.I it21239366 | 08/03/2026 | 01/01/2026 | 04/01/2026 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
qDBE5rNg4EO20fZfpmGeoskAHvbz | Perform integration with the platform | System Design & Development Phase | Completed | Medium | SANKALPA T W K S D it22564290 | Niwantha W.P.I it21239366 | 08/03/2026 | 01/02/2026 | 02/03/2026 | false | false | 19/03/2026 | SANKALPA T W K S D it22564290
qN0d3S_hGEOVMW44CNdzI8kAJSY6 | Integrate advisory recommendations (fertilization, pest control) | Model Development Phase | Completed | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 08/03/2026 | 07/12/2025 | 10/12/2025 | false | false | 17/03/2026 | Niwantha W.P.I it21239366
rbsTzsHuiUKEMbtvzeyJTckAFUOZ | Proposal Reports (drafts) | Research & Planning Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 | 10/08/2025 | 15/08/2025 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
sH8t2_xHZ06ui4g4bNBE78kAJCpD | Test for false positives/negatives | Testing & Evaluation Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244 | Niwantha W.P.I it21239366 | 08/03/2026 | 02/02/2026 | 10/02/2026 | false | false | 17/03/2026 | FERNANDO W.T.T.S. it22590244
sWmrM-O0Dk2gUOFaFxCooskAD1Yv | UAT with farmers | Testing & Evaluation Phase | Not started | Medium | Niwantha W.P.I it21239366 | Niwantha W.P.I it21239366 | 08/03/2026 |  | 04/04/2026 | false | false
tBWOXvozPk-S4G9JMvrgNskAAEmu | Meet with CRI (external supervisor) | Research & Planning Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 | 28/12/2025 | 28/12/2025 | false | false | 08/03/2026 | Niwantha W.P.I it21239366
wTqyHbBIxU2JA6hLowpf58kANsTK | Website Submission | Research & Planning Phase | Completed | Medium | Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 |  | 26/04/2026 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674
xudEqLDHSE-rEbqp1z0-tckAB46Y | Report monthly status | No Bucket | Completed | Medium |  | Niwantha W.P.I it21239366 | 07/03/2026 |  | 08/08/2026 | false | false | 19/03/2026 | SANKALPA T W K S D it22564290
ywMpneiub0OeH68L-dD0V8kAKGue | Research Paper | Research & Planning Phase | Completed | Medium | FERNANDO W.T.T.S. it22590244;SANKALPA T W K S D it22564290;Niwantha W.P.I it21239366;Prasangi W.K.K.I it21215674 | Niwantha W.P.I it21239366 | 07/03/2026 |  | 20/03/2026 | false | false | 08/03/2026 | Prasangi W.K.K.I it21215674

## Plan name
Plan name | CocoSmart - Final Year Research Project
Plan ID | QK_wYmqgekOJOxzluLyj0skAFalo
Date of export | 19/03/2026